## Tasks
Task Name | Progress | Priority | Assigned To | Completed Date
Submit the Demo (15 mins) | Not started | Urgent | Amlan Chowdhury;Shakif Malek;Monoarul ISLAM;Mohammad Rakibul Hasan;Humayoun Kabir Emon
Submit code for other teams to review | Not started | Urgent | Amlan Chowdhury;Shakif Malek;Humayoun Kabir Emon
Front end timestamp format is not correct | Not started | Medium
Replace Basic Auth with OAuth2 | Not started | Medium
Create Some Dummy Data | Not started | Medium
Get interested participants of a campaign API | Not started | Medium
Add restriction to de register from a campaign | Not started | Medium
Delete Campaign Image API | Completed | Medium | Humayoun Kabir Emon | 01/28/2020
Update Campaign Status API | Completed | Medium | Humayoun Kabir Emon | 01/28/2021
Users should not register with existing email | Not started | Medium | Mohammad Rakibul Hasan | 01/28/2022
Add campaign review API integration | Not started | Medium
Add campaign review | Not started | Medium | Monoarul ISLAM
Add campaign rating API integration | Not started | Medium | Monoarul ISLAM
Add campaign rating UX | Not started | Medium | Monoarul ISLAM
Search Campaign API integration | Completed | Medium | Amlan Chowdhury | 01/28/2021
Search Campaign UX | Completed | Medium | Amlan Chowdhury | 01/28/2021
Code formation lint | Not started | Medium
Fix edit campaign issue | Completed | Medium | Shakif Malek | 01/28/2021
Create API to get User's Created Campaign List | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
Delete Campaign API integration | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
Modify backend to perform Campaign Delete Operation | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
Add User Dashboard UI | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
Prevent taking duplicate username while signing up | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
Join Campaign API integration With UI | Completed | Medium | Mohammad Rakibul Hasan | 01/27/2021
API integration for edit campaign | Completed | Medium | Mohammad Rakibul Hasan | 01/25/2021
Admin Dashboard | Completed | Medium | Shakif Malek | 01/25/2021
Add campaign approval view | Completed | Medium | Shakif Malek | 01/25/2021
Add campaign approval API integration | Completed | Medium | Shakif Malek | 01/25/2021
Add Campaign Edit UX | Completed | Medium | Mohammad Rakibul Hasan | 01/24/2021
Create Campaign API integration | Completed | Medium | Shakif Malek | 01/20/2021
Update Base URL on front end | Completed | Urgent | Shakif Malek | 01/19/2021
Add Participants Limits in the UI | Completed | Medium | Mohammad Rakibul Hasan | 01/19/2021
Add Participants Limits and logic in the Backend | Completed | Medium | Mohammad Rakibul Hasan | 01/19/2021
Create Campaign UX | Completed | Medium | Shakif Malek | 01/13/2021
Update campaign approval API | Completed | Medium | Humayoun Kabir Emon | 01/08/2021
Search campaigns API | Completed | Medium | Humayoun Kabir Emon | 01/05/2021
API integration on Campaign Details View | Completed | Medium | Shakif Malek | 01/05/2021
Add Country States and City for specific location | Completed | Medium | Humayoun Kabir Emon | 12/29/2020
API routes should follow RESTful resource naming convention. | Completed | Important | Humayoun Kabir Emon | 12/28/2020
Reduce complexity of ProjectConfig | Completed | Medium | Humayoun Kabir Emon | 12/24/2020
Move image folder to resource | Completed | Medium | Humayoun Kabir Emon | 12/24/2020
Add weekly timesheet on repo | Completed | Medium | Shakif Malek | 12/21/2020
Web - I want see campaign details | Completed | Medium | Shakif Malek | 12/21/2020
Get campaign by approval id API | Completed | Medium | Humayoun Kabir Emon | 12/21/2020
List active/approved campaigns API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Rate a host API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Update host rating API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Delete host rating API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Delete a review API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Update reviews of a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Get all reviews of a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Add Reviews to a Campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
De register from a campaigns API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
List of participants of a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Join an active campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Update a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Delete a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Get Campaign Status API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Filter Campaigns by location API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Filter Campaigns by budgets API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
Filter Campaigns by host API | Completed | Medium | Humayoun Kabir Emon | 12/20/2020
I want to see active campaigns ( campaign list page) (Flutter) | Completed | Medium | Mohammad Rakibul Hasan | 12/17/2020
Apply styles on Login & Registration | Completed | Medium | Shakif Malek | 12/16/2020
Flutter Login/Registration mockup | Completed | Medium | Monoarul ISLAM | 12/11/2020
Flutter Registration UX | Completed | Medium | Mohammad Rakibul Hasan | 12/11/2020
Spring Security(Basic) | Completed | Medium | Amlan Chowdhury | 12/11/2020
I want to see all active campaigns | Completed | Medium | Humayoun Kabir Emon | 12/04/2020
Campaign UX | Completed | Medium | Shakif Malek | 12/04/2020
Iterate DB Schema Ratings | Completed | Medium | Humayoun Kabir Emon | 12/04/2020
Flutter Login UX | Completed | Medium | Mohammad Rakibul Hasan | 12/04/2020
Campaign List mockup | Completed | Medium | Monoarul ISLAM | 12/04/2020
Join a campaign UX | Completed | Medium | Humayoun Kabir Emon | 12/01/2020
Create a campaign API | Completed | Medium | Humayoun Kabir Emon | 12/01/2020
DB Schema | Completed | Medium | Humayoun Kabir Emon | 12/01/2020
Registration UX | Completed | Medium | Shakif Malek | 12/01/2020
Login UX | Completed | Medium | Shakif Malek | 12/01/2020
Login/Registration Mockup | Completed | Medium | Monoarul ISLAM | 12/01/2020
Add STAGE branch | Completed | Medium | Shakif Malek | 11/30/2020
Initiate React App | Completed | Important | Shakif Malek | 11/27/2020
Initiate Spring Boot App | Completed | Important | Humayoun Kabir Emon | 11/22/2020
Create GitLab Repository | Completed | Important | Shakif Malek | 11/22/2020
Start a landing page(static) | Completed | Medium | Monoarul ISLAM | 11/22/2020
Try demo Flutter App | Completed | Low | Mohammad Rakibul Hasan | 11/17/2020